## Sheet1
Claire Petras
ENGL 4740 UC Denver English Honors in Writing
Professor Rodney Herring
Spring 2013 |  | 1/22-1/27 | 1/28-2/3 | 2/4-2/10 | 2/11-2/17 | 2/18-2/24 | 2/25-3/3 | 3/4-3/10 | 3/11-3/17 | 3/18-3/24 | 3/25-3/31 | 4/1-4/7 | 4/8-4/14 | 4/15-4/21 | 4/22-4/28 | 4/29-5/5 | 5/6-5/12 | 5/13-5/18
[11 empty] | Spring | [6 empty] | Graduation!
Timeline |  | wk 1 | wk 2 | wk 3 | wk 4 | wk 5 | wk 6 | wk 7 | wk 8 | wk 9 | Break | wk 10 | wk 11 | wk 12 | wk 13 | wk 14 | wk 15 | wk 16
Deliverables | Design document |  |  | ✓
| Project Plan |  |  | ✓
| Design a style guide | [9 empty] | ✓
| Timeline |  |  |  |  | ✓
| Storyboarding |  |  |  |  | ✓
| Sitemap | [11 empty] | ✓
| Wireframes | [5 empty] | here
| Flowcharts | [5 empty] | here
| Content Inventory |  |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| Blog | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| Usability testing | [11 empty] | ✓ | ✓
| Second reader-Nicole | [13 empty] | here
| Submission-Rodney, Committee | [14 empty] | HERE!!
| Oral Defence | [14 empty] | HERE!!
2013-04-29 12:30
Design | conceptualize-how do I want to tell this story? |  |  |  |  | ✓
| page layout - post its |  |  |  |  | ✓
| define site colors, fonts, layout-style guide and CSS | [9 empty] | ✓
| storyboard the site by hand, scan |  |  |  |  | ✓
| define navigation for site-sitemap | [5 empty] | ✓
| determine layout grids for home, main pages-wireframe | [11 empty] | ✓
| document processes within site-flowcharts | [5 empty] | here
Build | home page-program layout, position, fonts, background, CSS | [6 empty] | ✓ | ✓ | ✓
| primary global nav, secondary global nav, submenus | [8 empty] | ✓ | ✓
| content for all pages, graphics, animation, multimedia | [10 empty] | ✓ | ✓
| draft up usability testing requirements (see project plan) | [11 empty] | ✓
| implement usability testing | [12 empty] | ✓ | ✓
| editing, fixing, extras | [12 empty] | ✓ | ✓
| draft up usability testing findings | [13 empty] | here
weekly | ready to go, paperwork, set up blog | ✓
completes | Dreamweaver, design ideas |  | ✓
| reading-wireframes, project planning |  |  | ✓
| project mgmt-doc design, project plan, timeline, content inventory |  |  |  | ✓
| conceptualize-layout, storyboards |  |  |  |  | ✓
| begin programming in Dreamweaver | [6 empty] | ✓